## Slide 1: INSTITUTIONAL REVIEWS Implementation process
Prof Nilanthi de Silva
Director QAC

## Slide 2: What happens before site visit?
QAC will assign reviewers to each University that has submitted an SER
QAC will obtain agreement of reviewers and consent from the VC for the Review Panel
Reviewers will be required to declare any possible conflict of interests and sign an agreement with UGC
QAC will organize a Pre-Review meeting with Reviewers assigned to specific universities and hand over the SERs (end June / first week of July)

## Slide 3: Before site visit…ctd
Each reviewer is expected to go through the assigned SER and carry out an individual desk evaluation
QAC will organize pre-site visit meeting (end July / early August), to enable review panels to compare their individual scores
Review panel is expected to agree on a Chairperson
Site visits will be scheduled during the months of August – December 2019
Site visit dates will be fixed with agreement from both Reviewers and universities

## Slide 4: Before site visit… ctd
Review chair is expected to contact VC / IQAU Director well before site visit and agree on tentative programme for site visit
UGC will arrange for transport and accommodation near the University under review

## Slide 5: What do we expect from reviewers? Key deliverables
Before site visit:
    Deliverable 1: Individual desk evaluation
After site visit – team reports submitted by Review Chair to QAC on behalf of Panel:
    Deliverable 2: Preliminary report
    Deliverable 3: Draft Review Report
    Deliverable 4: Final Review Report

## Slide 6: Deliverable 1. Desk evaluation
Each reviewer is expected to assess the SER and assign scores for each standard, based on what is given in the SER.
A pre-formatted Excel file will be provided for this purpose for scoring
Make notes on any items that you would like clarified during the site visit
Completed Excel file should be emailed to QAC before pre-site visit meeting

## Slide 7: Deliverable 2. Preliminary report
Should be compiled by Review Chair, based on contributions of all members of Review Panel
Precise format will be provided at pre-review meeting.
Needs to include:
  Summary information regarding university, review panel and site visit dates
  Key findings regarding strengths and weaknesses identified in relation to each review criterion
  Scores awarded for each standard, together with criterion-wise actual scores and final grade (use same preformatted Excel file)
RC to send to QAC by email within 2 wks of completing site visit

## Slide 8: Deliverable 3. Draft Review Report
Should be compiled by Review Chair, with contributions from all members of Review Panel
Format set out in Institutional Review Manual (p 103-6)
  Section 1: Introduction to university and review context
  Section 2: Observations on SER
  Section 3: Description of review process
  Section 4: University’s approach to quality and standards
  Section 5: Commentary on each of the 10 criteria
  Section 6: Grading of overall performance
  Section 7: Commendations and recommendations
  Section 8: Summary
  Annexures

## Slide 9: Deliverable 3 ctd
Details of cover page and formatting etc will be provided at Pre-Review meeting
Word limit: 12,000 words
Deadline for submission to QAC (by email): within 6 weeks of completing site visit
Draft report will be emailed by DQAC to VC, for corrections / comments (together with Excel file with detailed marks), to be sent back within 3 weeks

## Slide 10: Deliverable 4. Final Review Report
VC’s comments will be emailed to Review Chair, by DQAC for consideration in finalizing the Review Report
Review Chair should communicate with other members and decide on what consideration should be given to comments from VC
Deadline for submission of Final Report to QAC: within 3 weeks of receiving comments from VC
Final report will be sent back to VC for any further corrections / comments, to be sent back within 1 week

## Slide 11: Deliverable 4 ctd
QAC requires Final Report in Word and pdf formats, and a single hard copy with original signatures of review panel, as well as attendance sheets.
Payments vouchers will be sent to the UGC after receipt of hard copy
Payment for reviewers: Rs 66,000/- per review

## Slide 12: Process after site visit
Review Chair submits preliminary report within 2 weeks of completion of site visit, with key finding regarding each review criterion and the scores and final grade awarded by the Review Panel
Review Chair submits a comprehensive Draft Report within 6 weeks of completion of the site visit
DQAC forwards draft report and scores to VC with request for comments within 3 weeks
DQAC forwards any comments from VC to Review Chair, for consideration in finalizing report

## Slide 13: After site visit…
Review Chair submits Final Report to DQAC within 3 weeks of receiving comments from VC
DQAC forwards Final Report to VC for concurrence within 1 week. Any further factual inaccuracies may be pointed out for correction
DQAC forwards any further comments to Review Chair for consideration by the Team
Final Report from Review Chair is sent to Editorial Team for language checks and correction (if necessary)

## Slide 14: After site visit
Final Report published on QAC website after editing
Faculty develops Action Plan for implementation of recommendations in review report